## POD1
POD 1 — Pricing Agent Activities & Dependencies
Activity Group | Development Activity | Required Services / Tools | Technical Dependency | Comment
Core Multi-Agent Architecture | Orchestrator / supervisor agent design | LLM access; shared Dev/SIT/UAT environment | Agent framework already decided | these are steps through which agent is going to generate response
Core Multi-Agent Architecture | Sub-agent: Compute Agent | Secure API/tool calling connector | Pricing logic spreadsheet/API | these are steps through which agent is going to generate response
Core Multi-Agent Architecture | Sub-agent: Sensitivity analysis agent | Sensitivity parameter configuration: accepted range of different parameters within which pricing should be tested | compute Agent, Pricing policy so that we know how much to stretch to identify room | these are steps through which agent is going to generate response
Core Multi-Agent Architecture | Sub-agent: Scenario simulation agent | Different scenario configuration | Compute Agent, Sensitivity agent already functional | these are steps through which agent is going to generate response
Core Multi-Agent Architecture | Sub-agent: Recommendation drafting agent | Recommendation templating; explanation/reasoning generation | Return calculation, sensitivity outputs and scenario outputs | these are steps through which agent is going to generate response
Core Multi-Agent Architecture | Sub-agent: Exception & approval routing agent | Policy rule engine; approval workflow integration | Pricing policy and delegated-authority rules documented by FAB | these are steps through which agent is going to generate response
Core Multi-Agent Architecture | Agent to Agent communication: Agent server/client build | A2A framework. This is because sensitivity and scenario agents will communicate with Compute agent | All sub-agents individually functional; orchestrator routing logic defined | these are steps through which agent is going to generate response
Core Multi-Agent Architecture | Agentic WorkFlow Building | Workflow builder, Compiler | all agents along with orchestrator created | these are steps through which agent is going to generate response
Core Multi-Agent Architecture | Tool / function-calling framework & tool registry | Tool/function schema definitions; tool registry service | Data product APIs and calculation engines exposed as callable tools | these are steps through which agent is going to generate response
Core Multi-Agent Architecture | Multi-turn conversation | Conversation orchestration / workflow engine | Strategy for multiturn conversation already identified like rolling summary etc | these are steps through which agent is going to generate response
Core Multi-Agent Architecture | Persisting State and Context management (short- and long-term) | Short term memory storage; Long term memory storage | Workflow design Completed | these are steps through which agent is going to generate response
Core Multi-Agent Architecture | Retreiving logic from stored conversations | Search service | Workflow design Completed | these are steps through which agent is going to generate response
Core Multi-Agent Architecture | Human in the loop for State update/ Approval | workflow interruption, Approval workflow UI; no-write-back safeguard | Identified steps where state is allowed to update and approval routing rules and delegated authority documented | these are steps through which agent is going to generate response
Core Multi-Agent Architecture | Evaluator | Automated grounding checks; LLM-as-judge verification step | Workflow design Completed | these are steps through which agent is going to generate response
Data Retrieval & Grounding — MCP Integration & RAG | MCP server/client build to retrieve governed data products | MCP server implementation; MCP client SDK | Tools and Functions already created
Data Retrieval & Grounding — MCP Integration & RAG | RAG Pipeline building | Document ingestion pipeline; Embedding model; vector database | FAB provides pricing policy documents
Data Retrieval & Grounding — MCP Integration & RAG | RAG Retrieval API | Hybrid (semantic + keyword) retrieval; re-ranking. | RAG Pipeline
Observability & telemetry | Instrumeting Agents, Tools, LLM and Data etc and passed on to POD 2 scope | Opentelemetry SDK | components identified and agreed
Observability & telemetry | Immutable audit logging of every recommendation (Complete trace) and passed on to POD 2 scope | Audit Log store | telemetry schema agreed
Guardrails | Input validation/PII/Senesitive-data redaction & prompt-injection defence | Input sanitisation layer; prompt-injection detection filters, Rules/policy engine integrated | Threat model for agent inputs agreed with Security
Guardrails | Output redaction | Output schema validation | Every output is mapped to a grounded numbers
Security & Governance | Authentication & authorization for agent-to-system calls | Service-to-service auth (OAuth/mTLS); role-based access control | Security architecture and identity provider integration confirmed
Feedback System & Continuous Learning | User feedback capture (accept / override / reject with reason) | Feedback UI component; Structured Pointers for feedback eg: No of steps taken etc | Workflow UI available
Feedback System & Continuous Learning | Feedback-to-eval pipeline (override analysis) | Feedback storage | Feedback capture live; golden eval set established
Feedback System & Continuous Learning | Prompt/guardrail refinement loop from feedback signal | Prompt version control; change-approval workflow | Feedback-to-eval pipeline operational
Feedback System & Continuous Learning | Divergence tracking (recommendation vs. final approved price) | Divergence analytics dashboard | Final approval outcomes captured and mapped to original recommendation
Evaluation — Development / Pre-Production | Golden evaluation set construction | Curated set of representative pricing scenarios with expected outputs | Historical pricing & outcomes data available
Evaluation — Development / Pre-Production | Red-team / adversarial testing (jailbreak, guardrail bypass) | Adversarial test-case library; scheduled red-team exercises | Guardrail policy engine in place
Evaluation — Development / Pre-Production | Benchmark against human pricing decisions | Backtesting harness against historical deals | Historical deal outcomes and rationale available and labelled
Monitoring — Production | Production performance monitoring (latency, success rate, throughput) | Application performance monitoring integrated with GERNAS observability platform | POD 2 agent-runtime telemetry instrumentation complete
Monitoring — Production | Cost / token-usage monitoring per agent, pod and scenario | Usage metering dashboard | Telemetry pipeline captures token/cost signal (POD 2)
Monitoring — Production | Model / output drift monitoring vs. golden baseline | Drift-detection job scheduled against production traffic sample | Golden eval set and baseline metrics established
Monitoring — Production | Anomaly detection & alerting on agent behaviour | Anomaly-detection rules/models; alerting integration | Baseline behaviour profile established from UAT traffic
Monitoring — Production | Live dashboard for override rate, escalation rate, guardrail triggers | GERNAS dashboards | Feedback and guardrail telemetry already implemented
User Interface | API / integration layer exposing the agent to front-end channels | API gateway; authentication; rate limiting | Front-end/UX design agreed (chat interface integrated in GERNAS or STRATUS Platform)
User Interface | UI Components: Executive Console, drill down and scenario workspace | Front-end UI framework; role-based access control; dashboard, drill-down and scenario-visualization components | Approved UX designs; API / integration layer complete; pricing, sensitivity and scenario outputs available

## POD2
POD 2 — GERNAS Telemetry Activities & Dependencies
Activity Group | Development Activity | Required Services / Tools | Technical Dependency
Cross-Layer Telemetry Foundation | Build separate decorator templates for the Infrastructure, Agent Runtime and Compliance layers, reusable to create component-specific tracing decorators within each layer | Shared decorator framework/SDK; standard telemetry and audit schemas; logging, metrics and tracing libraries; template configuration and testing tools | Component interfaces and trace points identified across all three layers; telemetry standards, event schemas and integration contracts agreed with POD 1 and POD 3
Infrastructure Layer | Compute & hosting health monitoring (AKS) | Infra metrics agent (CPU, memory, disk, container/pod health) | Access to Dev/SIT/UAT and Production hosting configuration
Infrastructure Layer | Deployed endpoints | Network latency/error monitoring between services, MCP endpoints and data sources | Network topology documented by platform architects
Infrastructure Layer | Environment-aware monitoring (shared Dev/SIT/UAT namespace vs. isolated Production) | Environment-tagging in all infra telemetry; separate dashboards per environment | Environment strategy confirmed (shared namespace boundaries, isolation rules)
Infrastructure Layer | Capacity planning & autoscaling telemetry | Utilisation trend dashboards; scaling-event logs | Baseline load established from early sprints
Infrastructure Layer | Infrastructure cost monitoring | Cloud cost/usage export integrated into telemetry pipeline | Billing/usage export access from platform team
Agent Runtime Layer | Agent invocation & reasoning-step tracing | Distributed tracing (OpenTelemetry) across orchestrator and sub-agents | Agent/orchestrator code instrumentable; correlation-ID scheme agreed
Agent Runtime Layer | Tool / MCP call tracing | Tool-call span instrumentation; MCP request/response logging | MCP integration (POD 1) functional
Agent Runtime Layer | A2A message tracing across sub-agents | Message-bus tracing; correlation across agent hops | A2A integration (POD 1) functional
Agent Runtime Layer | LLM call metrics: tokens, latency, cost per call | Model-provider usage metrics integration | Model management / provider routing (POD 1) in place
Agent Runtime Layer | RAG retrieval telemetry (retrieval latency, relevance, hit rate) | Retrieval-quality metrics pipeline | RAG implementation (POD 1) functional
Agent Runtime Layer | Conversation / session-level telemetry | Session tracking across multi-turn interactions | Memory & context management (POD 1) functional
Agent Runtime Layer | Error, exception & retry tracking | Error-rate dashboards; retry/backoff logging | Instrumentation baseline in place across agent runtime
Agent Runtime Layer | Human override & escalation event tracking | Override-event capture wired into telemetry schema | Feedback system (POD 1) functional
Agent Runtime Layer | Model / output drift signal collection | Drift-metric collection feeding POD 1's monitoring layer | Golden eval baseline established (POD 1)
Agent Runtime Layer | Data products access tracing | Data-product access logs integrated into the telemetry pipeline | POD 3 data products expose access/audit events and stable identifiers
Compliance Layer | Immutable audit trail across agent, data and decision chain | Append-only, tamper-evident log store | Governed semantic layer / unified schema agreed across all telemetry sources
Compliance Layer | Data lineage & access logging | Lineage tracking from data product through to agent output | POD 3 data product contracts finalised
Compliance Layer | PII / data-privacy monitoring | PII-access monitoring and alerting | Data classification policy confirmed (linked to POD 1 governance)
Compliance Layer | Guardrail-violation & policy-adherence logging | Guardrail-event capture from POD 1 policy engine | Guardrail policy engine (POD 1) functional
Compliance Layer | Approval-workflow audit logging | Approval-chain capture (who approved, when, on what evidence) | Human-in-the-loop approval enforcement (POD 1) functional
Compliance Layer | Security event monitoring (auth failures, anomalous access) | SIEM integration or equivalent security event pipeline | Authentication/authorization layer (POD 1) functional
Compliance Layer | Retention & archival policy enforcement | Automated retention/archival jobs per data/telemetry class | FAB records-retention policy confirmed
Compliance Layer | Regulatory / ARB reporting hooks | Report generation against audit trail and compliance telemetry | ARB reporting format and cadence agreed with FAB
Telemetry Data Pipeline | Collect telemetry from Infrastructure, Agent Runtime and Compliance components using the layer-specific decorators | Telemetry collectors/agents; OpenTelemetry SDK and Collector; log, metric and trace exporters; secure service endpoints | Layer-specific decorator templates implemented; component trace points identified; environment and correlation identifiers standardized
Telemetry Data Pipeline | Post-process and enrich collected telemetry through validation, normalization, correlation, masking and aggregation | Stream-processing framework; schema validation and transformation rules; correlation engine; PII masking and enrichment services | Unified telemetry schemas and data-classification rules agreed; reliable timestamps, component IDs and correlation IDs available
Telemetry Data Pipeline | Ingest processed telemetry into operational, analytical and audit data stores | Message broker/event bus; ingestion pipelines; metrics, log, trace and audit stores; retry and dead-letter handling | Target storage architecture, access controls, retention policies and environment-specific ingestion endpoints provisioned
Telemetry Visualization | Build dashboards, alerts and drill-down views for Infrastructure, Agent Runtime and Compliance telemetry | Dashboard and visualization platform; query/semantic layer; alerting engine; role-based access controls; reusable dashboard templates | Processed telemetry available in queryable stores; KPIs, thresholds, user roles and dashboard requirements agreed with stakeholders

## POD3
Activity Group | Development Activity | Required Services / Tools | Technical Dependency | Comment
Data Discovery | Confirm source systems and data owners | MDP catalogue; source documentation | Approved MVP scope; business data requirements | Prefer MDP where the required source is available
Data Discovery | Profile source data and validate sample availability | Azure Databricks notebooks; Databricks SQL | Source or MDP access; representative sample data | Capture volume, schema, nulls, duplicates and anomalies
Data Discovery | Define data contract and source expectations | Data contract template; collaboration repository | Source schema; refresh frequency; data owner inputs | Include schema, SLA, quality and security expectations
Data Design | Design source-to-Bronze ingestion flow | Azure Databricks; Delta Lake; Unity Catalog | Approved data contract; source connectivity | Document batch or incremental ingestion approach
Data Design | Define Delta table schema, partitioning and optimization approach | Delta Lake; Unity Catalog | Source profile; expected volume and query patterns | Keep the design proportionate to MVP scale
Data Design | Define load, restart and recovery strategy | Databricks Workflows; Delta Lake | Load frequency; source change pattern; recovery expectations | Specify append, upsert or SCD behavior
Data Design | Complete source-to-target mapping | Mapping template; business glossary | Source schema; Bronze/Silver/Gold target models | Map data type, default, derivation and rejection rules
Data Design | Define data quality and reconciliation rules | Databricks notebooks or SQL; DQ framework | Business critical fields; source totals; acceptance thresholds | Business team validates business rules and thresholds
Data Design | Define access control, classification and lineage | Unity Catalog; Microsoft Entra ID | Data classification; user groups; least-privilege model | Include sensitive-data handling and object-level permissions
Ingestion Build | Develop reusable Bronze ingestion notebook or module | Azure Databricks notebooks; PySpark or SQL; Delta Lake | Approved ingestion design; accessible source | No configuration file dependency for this MVP
Ingestion Build | Implement schema validation and standardization | Azure Databricks; Delta Lake | Data contract; source-to-target mapping | Handle schema mismatch and rejected records
Ingestion Build | Implement incremental loading and idempotent restart | Databricks Workflows; Delta Lake | Incremental key or watermark; restart design | Prevent duplicate processing on rerun
Ingestion Build | Implement audit logging, exception handling and reconciliation | Databricks job logs; Delta audit tables | Control totals; error-handling standards | Capture run ID, counts, status and error details
Curation Build | Build Silver cleansing and standardization transformations | Azure Databricks; PySpark or SQL; Delta Lake | Bronze data; mapping and quality rules | Standardize formats, cleanse and deduplicate
Curation Build | Implement business keys, reference mappings and SCD logic | Delta Lake; reference data sources | Approved business keys; reference data; history requirement | Business team reviews matching and history rules
Curation Build | Publish curated/base data product | Unity Catalog; Delta Lake | Completed Silver transformations; technical tests | Register metadata, ownership and consumption guidance
Composition Build | Build Gold business transformations and aggregations | Azure Databricks; Databricks SQL; Delta Lake | Curated data product; approved business logic | Trace each derived field to an agreed rule
Composition Build | Create consumption-ready tables and views | Databricks SQL; Unity Catalog | Confirmed consumer pattern and access model | Use semantic output only if confirmed for the MVP
Composition Build | Optimize MVP queries and table layout | Databricks SQL; Delta optimization capabilities | Representative queries; expected workload | Capture baseline and post-optimization observations
Integration & Security | Configure service connectivity using approved identity pattern | Managed Identity; APIM; Azure Key Vault where required | Endpoint details; identity and security approvals | Prefer Managed Identity; avoid embedded credentials
Integration & Security | Validate permissions and negative-access scenarios | Unity Catalog; Microsoft Entra ID | Approved role matrix; test identities | Infra and data platform teams review access behavior
Testing | Create and execute unit tests | Databricks notebooks; approved test framework | Completed code; synthetic or approved test data | Cover transformation, error and restart paths
Testing | Execute system integration testing | Azure Databricks; source and downstream endpoints | Integrated pipeline; SIT test cases; expected results | Use the agreed shared Dev namespace for SIT
Testing | Execute end-to-end data reconciliation | Databricks SQL; reconciliation queries | Source totals; Bronze, Silver and Gold outputs | Record variances, causes and resolution
Testing | Support business UAT and show-and-tell | Databricks SQL; dashboards or query outputs | Technical test exit; business scenarios; sample data | Use the agreed shared Dev namespace for UAT
Testing | Resolve defects and prepare test exit evidence | GitLab issues; test evidence repository | Defect log; retest results; residual risks | Obtain data platform and business acceptance
CI/CD & Release | Create build and deployment pipeline | GitLab CI/CD; Azure Databricks deployment tooling | Repository; environment variables; deployment permissions | Align with the DevOps-managed pipeline
CI/CD & Release | Configure code quality and merge controls | GitLab; linting and test tools | Branching standard; reviewer list; quality gates | Require peer review before merge
CI/CD & Release | Prepare release notes, implementation and rollback plan | Release templates; GitLab | Approved UAT; deployment sequence; support contacts | Configuration file is intentionally omitted
CI/CD & Release | Deploy MVP assets and permissions | GitLab CI/CD; Azure Databricks; Unity Catalog | Release approval; production or confirmed target environment | Deploy notebooks, jobs, tables, views and grants
CI/CD & Release | Execute post-deployment smoke test and reconciliation | Azure Databricks; Databricks SQL | Successful deployment; test checklist | Confirm schedules, access and business output
Operations & Handover | Configure monitoring, alerting and run logging | Azure Monitor or approved observability platform; Databricks job monitoring | Operational thresholds; support distribution list | Assess agent observability only where applicable