## How to read this
How to read this workbook
This is the original 'Development Activities' with a plain-English column added beside each column.
Blue headers = original columns. Green headers = plain-English helper columns.
What each ORIGINAL column means:
Activity Group | The category / bucket the task belongs to - like a chapter heading grouping related tasks.
Development Activity | The actual specific task to build or do - the real piece of work.
Required Services / Tools | What you need in hand to do that task - software, platforms, services.
Technical Dependency | What must already be finished or in place BEFORE you can start this task (the prerequisite).
Comment | A free-text note or remark about the row.
Sheets:
POD1 | The Pricing Agent app - building the AI agents, data, guardrails, feedback, monitoring and UI.
POD2 | The GERNAS telemetry/observability platform - the 'beacon_kit'-style monitoring across 3 layers.
POD3 | The data products on Databricks - Bronze/Silver/Gold data pipelines, testing and release.

## POD1
Activity Group | (plain) What this group is | Development Activity | (plain) What this task means | Required Services / Tools | (plain) What you'd need | Technical Dependency | (plain) What must be ready first | Comment
Core Multi-Agent Architecture | Building the AI agents and how they work together. | Orchestrator / supervisor agent design | Design the 'boss' agent that directs all the others. | Microsoft Agent Framework (MAF) WorkflowBuilder; Groq (OpenAI-compatible) LLM; shared Dev/SIT/UAT AKS namespace | MAF's workflow builder, a Groq LLM, and a shared AKS test environment. | MAF chosen as the agent framework (already decided) | MAF is the chosen framework. | these are steps through which agent is going to generate response
Core Multi-Agent Architecture | Building the AI agents and how they work together. | Sub-agent: Compute Agent | An agent that does the actual pricing calculations. | MAF Agent with tool/function calling; secure MCP StreamableHTTP connector to the pricing API | A MAF agent with a secure MCP connector to the pricing API. | Pricing logic exposed as an MCP tool/API (e.g. DataLayer-as-a-Service) | The pricing logic is exposed as an MCP tool/API. | these are steps through which agent is going to generate response
Core Multi-Agent Architecture | Building the AI agents and how they work together. | Sub-agent: Sensitivity analysis agent | An agent that tests how the price reacts to changes. | MAF Agent; sensitivity parameter config (accepted value ranges) | A MAF agent plus the allowed value-range settings. | Compute Agent and FAB pricing policy available | The compute agent and pricing policy exist. | these are steps through which agent is going to generate response
Core Multi-Agent Architecture | Building the AI agents and how they work together. | Sub-agent: Scenario simulation agent | An agent that runs different what-if scenarios. | MAF Agent; scenario configuration | A MAF agent plus scenario setups. | Compute and Sensitivity agents functional | The compute and sensitivity agents work. | these are steps through which agent is going to generate response
Core Multi-Agent Architecture | Building the AI agents and how they work together. | Sub-agent: Recommendation drafting agent | An agent that writes the final recommendation with reasons. | MAF Agent; response templating with <llm_reasoning> capture | A MAF agent that drafts recommendations with captured reasoning. | Compute, sensitivity and scenario outputs available | The calculation, sensitivity and scenario results are ready. | these are steps through which agent is going to generate response
Core Multi-Agent Architecture | Building the AI agents and how they work together. | Sub-agent: Exception & approval routing agent | An agent that sends exceptions to the right approver. | MAF Agent; RBAC role_permissions matrix; HITL approval_store workflow | A MAF agent with the role matrix and human-approval workflow. | FAB delegated-authority rules documented; HITL approval store in place | Authority rules documented and the approval store exists. | these are steps through which agent is going to generate response
Core Multi-Agent Architecture | Building the AI agents and how they work together. | Agent to Agent communication: Agent server/client build | Let the agents send work to each other. | Google A2A (agent_framework.a2a.A2AAgent) over JSON-RPC/HTTP; A2A trace-context middleware | Google A2A messaging over HTTP with trace-context passing. | All sub-agents hosted as A2A nodes; orchestrator routing defined | Every sub-agent runs as an A2A node and routing is defined. | these are steps through which agent is going to generate response
Core Multi-Agent Architecture | Building the AI agents and how they work together. | Agentic Workflow Building | Wire all the agents together into one flow. | MAF WorkflowBuilder; typed Executor nodes; MeshState dataclass | MAF's workflow builder wiring typed executor steps. | All agents plus orchestrator created | All agents plus the orchestrator are built. | these are steps through which agent is going to generate response
Core Multi-Agent Architecture | Building the AI agents and how they work together. | Tool / function-calling framework & tool registry | Let agents call tools, with a catalogue of them. | MAF function-calling; node_registry / AGENT_REGISTRY; MCP tool factories | MAF tool-calling with an agent/tool registry and MCP tool factories. | Data-product APIs and calc engines exposed as MCP/callable tools | Data APIs and engines are exposed as callable tools. | these are steps through which agent is going to generate response
Core Multi-Agent Architecture | Building the AI agents and how they work together. | Multi-turn conversation | Handle back-and-forth conversations. | MAF workflow engine; rolling-summary strategy | The MAF workflow engine with a rolling-summary approach. | Multi-turn strategy (rolling summary) chosen | A multi-turn strategy (rolling summary) is chosen. | these are steps through which agent is going to generate response
Core Multi-Agent Architecture | Building the AI agents and how they work together. | Persisting State and Context management (short & long term) | Remember conversation context, short and long term. | ConversationStore; JSONL backend (Redis backend stub); rolling summarizer | A conversation store (JSONL now, Redis later) with a rolling summarizer. | Workflow design complete | The workflow design is done. | these are steps through which agent is going to generate response
Core Multi-Agent Architecture | Building the AI agents and how they work together. | Retrieving logic from stored conversations | Search past conversations to reuse them. | Conversation search over stored JSONL sessions | Search over stored conversation sessions. | Workflow design complete; conversation persistence live | Workflow design done and conversations are being stored. | these are steps through which agent is going to generate response
Core Multi-Agent Architecture | Building the AI agents and how they work together. | Human in the loop for State update / Approval | Let a human pause, approve or update mid-flow. | MAF workflow interruption; HITL approval_store + checkpoints; no-write-back safeguard | MAF pause/resume with an approval store, checkpoints and a no-overwrite safeguard. | Approval points and delegated-authority rules documented | The approval points and authority rules are documented. | these are steps through which agent is going to generate response
Core Multi-Agent Architecture | Building the AI agents and how they work together. | Evaluator | Auto-check the AI's answers are grounded and correct. | LLM-as-judge; grounding checks; workflow_evaluations suite | An AI-judge with grounding checks and the evaluation suite. | Workflow design complete | The workflow design is done. | these are steps through which agent is going to generate response
Data Retrieval & Grounding - MCP Integration & RAG | Getting trusted data and documents into the agents. | MCP server/client build to retrieve governed data products | Connect to governed data through MCP. | MCP StreamableHTTP server/client (DataLayer :9100, RAG :9000) | MCP StreamableHTTP server/client to the data and RAG services. | Tools and functions already created | The tools and functions already exist.
Data Retrieval & Grounding - MCP Integration & RAG | Getting trusted data and documents into the agents. | RAG Pipeline building | Ingest documents so agents can search them. | gernas_rag ingestion; embedding model; Qdrant vector DB; chunking | The RAG ingestion pipeline with an embedding model and Qdrant. | FAB provides pricing policy documents | FAB supplies the pricing policy documents.
Data Retrieval & Grounding - MCP Integration & RAG | Getting trusted data and documents into the agents. | RAG Retrieval API | An API to fetch the best-matching document chunks. | Hybrid semantic+keyword retrieval; cross-encoder re-ranking; REST :8000 / MCP :9000 | Combined smart+keyword search with re-ranking, exposed via REST/MCP. | RAG pipeline built and indexed | The RAG pipeline exists and is indexed.
Observability & telemetry | Adding tracking so POD 2 can monitor the system. | Instrumenting Agents, Tools, LLM and Data (passed to POD 2) | Add trackers to agents/tools/LLM/data for POD 2. | Beacon Kit decorators (traced_agent/tool/llm/a2a/mcp); OpenTelemetry SDK | Beacon Kit's tracking decorators on the OpenTelemetry SDK. | Instrumentation points identified and agreed with POD 2 | The parts to track are agreed with POD 2.
Observability & telemetry | Adding tracking so POD 2 can monitor the system. | Immutable audit logging of every recommendation (passed to POD 2) | Keep an unchangeable record of every recommendation. | Beacon Kit compliance module; HMAC-chained JSONL audit store | Beacon Kit's tamper-evident (hash-chained, signed) audit log. | Telemetry/audit schema agreed with POD 2 | The audit data format is agreed with POD 2.
Guardrails | Safety filters on inputs and outputs. | Input validation / PII redaction & prompt-injection defence | Filter bad or sensitive inputs and block prompt-injection. | deterministic_filters (regex PII/injection); Beacon guardrail_check events | Regex-based input filters emitting Beacon guardrail events. | Threat model for agent inputs agreed with Security | Security has agreed the threat model for inputs.
Guardrails | Safety filters on inputs and outputs. | Output redaction | Clean sensitive info out of the outputs. | Output PII redaction; output schema validation | PII redaction plus output-format validation. | Every output mapped to grounded numbers | Every output maps to a grounded number.
Security & Governance | Login, permissions and control. | Authentication & authorization for agent-to-system calls | Secure and permission the system calls. | Identity provider (mock now, real IdP later); RBAC role_permissions matrix; OAuth/mTLS | An identity provider plus the role matrix and secure service auth. | Security architecture and IdP integration confirmed | Security setup and identity provider are confirmed.
Feedback System & Continuous Learning | Learning from user feedback over time. | User feedback capture (accept / override / reject with reason) | Let users accept, override or reject with a reason. | feedback/store; React frontend feedback UI (accept/override/reject) | A feedback store plus the React UI for accept/override/reject. | Workflow UI (React frontend) available | The React workflow UI exists.
Feedback System & Continuous Learning | Learning from user feedback over time. | Feedback-to-eval pipeline (override analysis) | Turn user feedback (overrides) into test data. | Feedback store feeding workflow_evaluations replay set | Feedback feeding the evaluation replay set. | Feedback capture live; golden eval set established | Feedback is live and a golden set exists.
Feedback System & Continuous Learning | Learning from user feedback over time. | Prompt/guardrail refinement loop from feedback | Improve prompts and guardrails using feedback. | Prompt version control (my_KB/prompts); change-approval workflow | Versioned prompts with a change-approval process. | Feedback-to-eval pipeline operational | The feedback-to-eval pipeline works.
Feedback System & Continuous Learning | Learning from user feedback over time. | Divergence tracking (recommendation vs final approved price) | Track recommended price vs the final approved price. | Divergence analytics (recommended vs approved) on GERNAS dashboards | Analytics of recommended vs approved price on GERNAS. | Final approval outcomes captured and mapped to recommendation | Final approvals are linked to recommendations.
Evaluation - Development / Pre-Production | Testing quality before go-live. | Golden evaluation set construction | Build a trusted test set with expected answers. | workflow_evaluations curated scenarios with expected outputs | A curated evaluation set with expected answers. | Historical pricing & outcomes data available | Past pricing/outcome data is available.
Evaluation - Development / Pre-Production | Testing quality before go-live. | Red-team / adversarial testing (jailbreak, guardrail bypass) | Deliberately try to break the guardrails. | workflow_evaluations redteam mode; adversarial/jailbreak test library | The red-team evaluation mode with a jailbreak test library. | Guardrail policy engine in place | The guardrail engine exists.
Evaluation - Development / Pre-Production | Testing quality before go-live. | Benchmark against human pricing decisions | Compare AI pricing to human pricing on past deals. | workflow_evaluations benchmark/backtesting harness on historical deals | A backtesting harness replaying historical deals. | Labelled historical deal outcomes available | Past deal outcomes are labelled and available.
Monitoring - Production | Watching the system once it is live. | Production performance monitoring (latency, success, throughput) | Watch live speed, success rate and volume. | Beacon Kit metrics + traces exported to GERNAS (Grafana / Azure Monitor) | Beacon Kit metrics/traces feeding GERNAS dashboards. | POD 2 agent-runtime instrumentation complete | POD 2's agent tracking is finished.
Monitoring - Production | Watching the system once it is live. | Cost / token-usage monitoring per agent, pod and scenario | Watch spend and token use per agent/scenario. | Beacon Kit LLM token metrics + per-model cost table; usage dashboard on GERNAS | Beacon Kit token+cost metrics on a GERNAS usage dashboard. | POD 2 telemetry captures token/cost signal | POD 2 captures token/cost data.
Monitoring - Production | Watching the system once it is live. | Model / output drift monitoring vs golden baseline | Detect the AI drifting away from the known-good baseline. | Drift-detection job vs golden baseline (Beacon drift signals) | A drift-detection job using Beacon's drift signals vs the baseline. | Golden eval set and baseline metrics established | The golden set and baseline exist.
Monitoring - Production | Watching the system once it is live. | Anomaly detection & alerting on agent behaviour | Alert when agent behaviour looks abnormal. | Anomaly rules/models on GERNAS; alerting integration | Anomaly rules on GERNAS with alerting. | Baseline behaviour profile from UAT established | A normal-behaviour baseline from UAT exists.
Monitoring - Production | Watching the system once it is live. | Live dashboard for override rate, escalation rate, guardrail triggers | A live board of override, escalation and guardrail rates. | GERNAS dashboards over Beacon guardrail/override telemetry | GERNAS dashboards on Beacon's guardrail/override data. | Feedback and guardrail telemetry implemented | Feedback and guardrail tracking is built.
User Interface | The screens users interact with. | API / integration layer exposing the agent to front-end channels | Expose the agent to the front-end channels. | Starlette/uvicorn API + SSE (api_server.py :8000); API gateway; rate limiting | The Starlette streaming API, behind a gateway with rate limits. | Front-end/UX design agreed | The front-end/UX design is agreed.
User Interface | The screens users interact with. | UI Components: Executive Console, drill-down and scenario workspace | Build the console, drill-down and scenario screens. | React 18 + Vite + Tailwind frontend; RBAC; drill-down/scenario components | The React (Vite/Tailwind) front-end with access control and drill-down views. | Approved UX designs; API layer complete; outputs available | Designs approved, API done, and outputs are available.

## POD2
Activity Group | (plain) What this group is | Development Activity | (plain) What this task means | Required Services / Tools | (plain) What you'd need | Technical Dependency | (plain) What must be ready first
Cross-Layer Telemetry Foundation | Reusable building blocks all monitoring pieces are made from. | Build separate decorator templates for Infrastructure, Agent Runtime and Compliance layers | Build reusable 'stickers' that add tracking to any component. | Beacon Kit-style decorator framework (traced_agent/tool/llm/a2a/mcp, compliance_gate, guardrail_check); OTel SDK; shared telemetry & audit schemas | A Beacon-Kit-style decorator toolkit on the OTel SDK, with agreed data/audit formats. | Trace points identified across all 3 layers; semantic conventions & schemas agreed with POD 1 and POD 3 | Know where to attach trackers and agree the naming conventions with POD 1 & POD 3.
Infrastructure Layer | Watching the servers/machines the system runs on. | Compute & hosting health monitoring (AKS) | Watch server CPU, memory, disk and container health. | OTel Collector host + k8s (kubelet) receivers; Azure Monitor Container Insights / Prometheus | OTel Collector infra receivers feeding Azure Monitor/Prometheus. | Access to AKS Dev/SIT/UAT & Prod hosting config (infra/provisioning team owns the servers) | Access to the AKS setup (the infra team owns the servers).
Infrastructure Layer | Watching the servers/machines the system runs on. | Deployed endpoints | Watch the speed and errors of connections between services. | Client-span latency/error on A2A & MCP calls (Beacon); service-mesh / network metrics | Beacon client-span timings on A2A/MCP calls, plus network metrics. | A2A & MCP endpoints deployed; network topology documented | The A2A/MCP endpoints are deployed and the network map exists.
Infrastructure Layer | Watching the servers/machines the system runs on. | Environment-aware monitoring (shared Dev/SIT/UAT vs isolated Production) | Tell test data apart from live data on separate screens. | deployment.environment resource attribute; env-scoped OTLP routing; per-env Grafana/Azure dashboards | An environment tag on every signal, routed to per-environment dashboards. | Environment strategy confirmed (shared Dev/SIT/UAT namespace vs isolated Prod) | Agreement on how test vs live environments are separated.
Infrastructure Layer | Watching the servers/machines the system runs on. | Capacity planning & autoscaling telemetry | Track usage trends and when the system adds servers. | OTel Collector k8s metrics (HPA/replica/utilisation); scaling-event logs | Cluster utilisation and autoscaling-event metrics via the Collector. | Baseline load established from early sprints | A known normal load from early work.
Infrastructure Layer | Watching the servers/machines the system runs on. | Infrastructure cost monitoring | Track how much the cloud is costing. | Azure Cost Management / cloud billing export into the telemetry pipeline | A cloud-cost feed pulled into the pipeline (FinOps/infra owns the bill). | Billing/usage export access from the platform team | Permission to pull billing data.
Agent Runtime Layer | Watching what the AI agents actually do. | Agent invocation & reasoning-step tracing | Record each step and decision an agent makes. | Beacon traced_agent (SERVER spans); OpenTelemetry distributed tracing across the MAF orchestrator & sub-agents; W3C trace context | Beacon's agent spans tracing every MAF orchestrator/sub-agent step. | MAF executors instrumentable; correlation-ID (baggage) scheme agreed | MAF steps can be tagged and a shared ID scheme is agreed.
Agent Runtime Layer | Watching what the AI agents actually do. | Tool / MCP call tracing | Record every tool call and data-fetch an agent makes. | Beacon traced_tool / traced_mcp_tool (CLIENT spans); MCP StreamableHTTP request/response logging | Beacon tool/MCP spans plus MCP request/response logging. | MCP integration (POD 1, StreamableHTTP) functional | POD 1's MCP StreamableHTTP works.
Agent Runtime Layer | Watching what the AI agents actually do. | A2A message tracing across sub-agents | Follow messages as agents pass work to each other. | Beacon traced_a2a_hop + A2ATraceContextMiddleware; W3C traceparent propagation | Beacon A2A-hop spans that keep the trace connected across agents. | A2A integration (POD 1, Google A2A) functional | POD 1's Google A2A messaging works.
Agent Runtime Layer | Watching what the AI agents actually do. | LLM call metrics: tokens, latency, cost per call | Measure words used, speed and cost of each AI call. | Beacon traced_llm_call; token capture from Groq/OpenAI usage; per-model cost table; beacon.llm.* metrics | Beacon LLM spans capturing tokens from the Groq response, plus a cost table. | Model/provider routing (POD 1, Groq via OpenAI-compat) in place | POD 1's Groq model routing is in place.
Agent Runtime Layer | Watching what the AI agents actually do. | RAG retrieval telemetry (latency, relevance, hit rate) | Measure how fast and how relevant document searches are. | Retrieval-quality metrics (latency, hit-rate, rerank scores); re-enable gernas_rag telemetry over Qdrant | Search-quality metrics (latency, hit-rate, rerank) from the Qdrant RAG. | RAG implementation (POD 1, Qdrant + reranker) functional | POD 1's Qdrant RAG works.
Agent Runtime Layer | Watching what the AI agents actually do. | Conversation / session-level telemetry | Group a whole user conversation together to view it. | Session-scoped spans/metrics keyed on baggage session_id; align with ConversationStore | Session-scoped tracking keyed on the conversation's session ID. | Memory & context management (POD 1, JSONL ConversationStore) functional | POD 1's JSONL memory works.
Agent Runtime Layer | Watching what the AI agents actually do. | Error, exception & retry tracking | Record failures and automatic retries. | Span error status + Beacon error counters; circuit_breaker gauge; retry/backoff signals (collaboration_tools) | Error-status spans, a circuit-breaker gauge and retry signals. | Instrumentation baseline in place across agent runtime | Basic tracking is already added across agents.
Agent Runtime Layer | Watching what the AI agents actually do. | Human override & escalation event tracking | Record when a human overrides or escalates the AI. | First-class OverrideEvent/escalation capture; guardrail_check(escalate); wired to HITL approval_store | Dedicated override/escalation events wired to the human-approval store. | Feedback & HITL system (POD 1) functional | POD 1's feedback/HITL works.
Agent Runtime Layer | Watching what the AI agents actually do. | Model / output drift signal collection | Collect signals that the AI's answers are changing. | Drift-signal collection feeding POD 1's drift-detection job vs golden baseline | Drift signals feeding POD 1's baseline-comparison job. | Golden eval baseline established (POD 1) | POD 1's known-good baseline exists.
Agent Runtime Layer | Watching what the AI agents actually do. | Data products access tracing | Record when agents read POD 3's data products. | Beacon MCP access spans on DataLayer-as-a-Service; POD 3 stable data-product IDs & access-audit events | Beacon access spans on the data service, referencing POD 3's data-product IDs. | POD 3 data products expose access/audit events and stable identifiers (Unity Catalog) | POD 3 provides access events and permanent data IDs from Unity Catalog.
Compliance Layer | Keeping tamper-proof records for audit, privacy and regulators. | Immutable audit trail across agent, data and decision chain | Keep an unchangeable record across agents, data and decisions. | Beacon compliance module: SHA-256 hash-chain + HMAC-signed JSONL audit store; verify_chain | Beacon's hash-chained, signed, tamper-evident audit log. | Unified telemetry/audit schema agreed across sources | One agreed record format across all sources.
Compliance Layer | Keeping tamper-proof records for audit, privacy and regulators. | Data lineage & access logging | Trace data's journey from source to agent answer. | Unity Catalog lineage (POD 3-owned); Beacon references data-product IDs in spans/audit | Unity Catalog lineage (owned by POD 3); Beacon just references the IDs. | POD 3 data-product contracts finalised | POD 3's data agreements are finalised.
Compliance Layer | Keeping tamper-proof records for audit, privacy and regulators. | PII / data-privacy monitoring | Watch and alert on sensitive personal-data use. | PII detection (sanitizer/deterministic_filters) -> Beacon GuardrailEvent; alerting on GERNAS/SIEM | PII detection emitting Beacon events, with alerting on GERNAS/SIEM. | Data classification policy confirmed (Security) | Security's rules on sensitive data are confirmed.
Compliance Layer | Keeping tamper-proof records for audit, privacy and regulators. | Guardrail-violation & policy-adherence logging | Log every time a safety rule is broken. | Beacon guardrail_check -> GuardrailEvent (block/warn/escalate) | Beacon guardrail events for every block/warn/escalate. | Guardrail policy engine (POD 1 deterministic_filters) functional | POD 1's guardrail filters work.
Compliance Layer | Keeping tamper-proof records for audit, privacy and regulators. | Approval-workflow audit logging | Record who approved what, when and on what basis. | ApprovalEvent capture (who/when/evidence); serialize/restore_context for HITL checkpoints | Approval events (who/when/evidence) tied to HITL checkpoints. | HITL approval enforcement (POD 1 approval_store) functional | POD 1's human-approval step works.
Compliance Layer | Keeping tamper-proof records for audit, privacy and regulators. | Security event monitoring (auth failures, anomalous access) | Watch for login failures and suspicious access. | Beacon rbac_check -> RBACEvent + auth-failure events; export to Security SIEM (Sentinel/Splunk) | Beacon RBAC/auth-failure events exported to the Security team's SIEM. | Authentication/authorization layer (POD 1 identity + RBAC) functional | POD 1's login/permission system works.
Compliance Layer | Keeping tamper-proof records for audit, privacy and regulators. | Retention & archival policy enforcement | Auto keep-then-delete records per the rules. | Retention & rotation jobs on Beacon JSONL/file stores; policy from Security | Keep/archive/rotate jobs on the telemetry stores you run, per Security's policy. | FAB records-retention policy confirmed (Security/GRC) | FAB's record-keeping rules are confirmed.
Compliance Layer | Keeping tamper-proof records for audit, privacy and regulators. | Regulatory / ARB reporting hooks | Generate the reports that regulators require. | ARB report generator over the HMAC audit chain (extends html_reporter) | A regulator-format report generator over the audit chain. | ARB reporting format & cadence agreed with FAB (GRC) | Agreed report format and schedule with FAB.
Telemetry Data Pipeline | Moving the collected data from apps to storage. | Collect telemetry using the layer-specific decorators | Gather all the tracked data from every component. | Beacon exporters -> OTel Collector (OTLP gRPC/HTTP); Grafana (Tempo/Mimir/Loki) or Azure Monitor | Beacon exporters sending to the OTel Collector and Grafana/Azure Monitor. | Decorator templates implemented; correlation & env IDs standardized | Trackers are built and IDs standardized.
Telemetry Data Pipeline | Moving the collected data from apps to storage. | Post-process and enrich (validation, normalization, correlation, masking, aggregation) | Clean, link and mask the data after collecting it. | OTel Collector processors (validate/normalize/batch/attributes); PII masking (hashing/sanitizer); correlation via trace/baggage | Collector processors that clean, mask and correlate the data mid-flight. | Unified schemas & classification agreed; reliable timestamps/IDs available | Agreed formats/classification and reliable IDs.
Telemetry Data Pipeline | Moving the collected data from apps to storage. | Ingest processed telemetry into operational, analytical and audit stores | Load the processed data into its databases. | Tempo (traces) / Mimir (metrics) / Loki (logs) or Azure Monitor; JSONL audit store; Collector retry/DLQ | Trace/metric/log backends (Grafana stack or Azure Monitor) plus the audit store. | Target storage architecture, access controls & retention provisioned | Storage set up with access and retention rules.
Telemetry Visualization | Turning the data into dashboards and alerts. | Build dashboards, alerts and drill-down views (Infra, Agent Runtime, Compliance) | Build the screens and alerts people actually look at. | Grafana / GERNAS dashboards + alert rules over Tempo/Mimir/Loki; Beacon KPI/threshold contract; html_reporter for dev | GERNAS/Grafana dashboards & alerts from Beacon's KPI contract (HTML report for dev). | Processed telemetry queryable; KPIs, thresholds & roles agreed with stakeholders | Data is queryable and KPIs/thresholds are agreed.

## POD3
Activity Group | (plain) What this group is | Development Activity | (plain) What this task means | Required Services / Tools | (plain) What you'd need | Technical Dependency | (plain) What must be ready first | Comment
Data Discovery | Finding out what data exists and who owns it. | Confirm source systems and data owners | Confirm where the data comes from and who owns it. | MDP data catalogue; source system documentation | The enterprise data catalogue (MDP) and source docs. | Approved MVP scope; business data requirements | The MVP scope and data requirements are approved. | Prefer MDP where the required source is available
Data Discovery | Finding out what data exists and who owns it. | Profile source data and validate sample availability | Inspect the data and check a sample is available. | Azure Databricks notebooks; Databricks SQL | Databricks notebooks and SQL. | Source or MDP access; representative sample data | Access to the source and a representative sample. | Capture volume, schema, nulls, duplicates and anomalies
Data Discovery | Finding out what data exists and who owns it. | Define data contract and source expectations | Agree the data's shape, quality and delivery rules. | Data contract template; GitLab collaboration repo | A contract template and a shared GitLab repo. | Source schema; refresh frequency; data owner inputs | The source structure, refresh rate and owner input. | Include schema, SLA, quality and security expectations
Data Design | Planning how data will be shaped and moved. | Design source-to-Bronze ingestion flow | Plan how raw data lands in the first (Bronze) layer. | Azure Databricks; Delta Lake; Unity Catalog | Databricks, Delta Lake and Unity Catalog. | Approved data contract; source connectivity (Managed Identity) | Contract approved and the source connects securely. | Document batch or incremental ingestion approach
Data Design | Planning how data will be shaped and moved. | Define Delta table schema, partitioning and optimization | Plan the table structure and how to speed it up. | Delta Lake; Unity Catalog | Delta Lake and Unity Catalog. | Source profile; expected volume and query patterns | You know the data profile, volume and query patterns. | Keep the design proportionate to MVP scale
Data Design | Planning how data will be shaped and moved. | Define load, restart and recovery strategy | Plan how loads run, restart and recover from failure. | Databricks Workflows; Delta Lake (time travel) | Databricks Workflows and Delta Lake. | Load frequency; source change pattern; recovery expectations | You know load frequency, change pattern and recovery needs. | Specify append, upsert or SCD behavior
Data Design | Planning how data will be shaped and moved. | Complete source-to-target mapping | Map each source field to its target field. | Mapping template; business glossary | A mapping template and a business glossary. | Source schema; Bronze/Silver/Gold target models | The source structure and the three target models exist. | Map data type, default, derivation and rejection rules
Data Design | Planning how data will be shaped and moved. | Define data quality and reconciliation rules | Set the rules for good data and matching totals. | Databricks notebooks/SQL; DQ framework (Great Expectations / DLT expectations) | Databricks plus a data-quality framework. | Business-critical fields; source totals; acceptance thresholds | You know the key fields, totals and pass/fail thresholds. | Business team validates business rules and thresholds
Data Design | Planning how data will be shaped and moved. | Define access control, classification and lineage | Set who can access data, its sensitivity and its trail. | Unity Catalog (lineage, tags); Microsoft Entra ID | Unity Catalog (lineage & tags) and Entra ID. | Data classification; user groups; least-privilege; stable data-product IDs for POD 2 | Classification & user groups defined, and permanent data IDs exposed for POD 2 telemetry. | Include sensitive-data handling and object-level permissions
Ingestion Build | Building the load of raw data in (Bronze). | Develop reusable Bronze ingestion notebook or module | Build the reusable code that loads raw data in. | Azure Databricks notebooks; PySpark or SQL; Delta Lake | Databricks with PySpark/SQL and Delta Lake. | Approved ingestion design; accessible source | The ingestion design is approved and the source is reachable. | No configuration file dependency for this MVP
Ingestion Build | Building the load of raw data in (Bronze). | Implement schema validation and standardization | Check incoming data matches the expected shape. | Azure Databricks; Delta Lake (schema enforcement) | Databricks and Delta Lake schema enforcement. | Data contract; source-to-target mapping | The data contract and field mapping exist. | Handle schema mismatch and rejected records
Ingestion Build | Building the load of raw data in (Bronze). | Implement incremental loading and idempotent restart | Load only new data and rerun safely without duplicates. | Databricks Workflows; Delta Lake (MERGE) | Databricks Workflows and Delta MERGE. | Incremental key or watermark; restart design | An incremental key/watermark and a restart design. | Prevent duplicate processing on rerun
Ingestion Build | Building the load of raw data in (Bronze). | Implement audit logging, exception handling and reconciliation | Log runs, handle errors and check totals match. | Databricks job logs; Delta audit tables | Databricks job logs and Delta audit tables. | Control totals; error-handling standards | Known control totals and error-handling standards. | Capture run ID, counts, status and error details
Curation Build | Cleaning and standardizing data (Silver). | Build Silver cleansing and standardization transformations | Clean and standardize the raw data. | Azure Databricks; PySpark or SQL; Delta Lake | Databricks with PySpark/SQL and Delta Lake. | Bronze data; mapping and quality rules | Bronze data plus mapping and quality rules exist. | Standardize formats, cleanse and deduplicate
Curation Build | Cleaning and standardizing data (Silver). | Implement business keys, reference mappings and SCD logic | Add business keys and track historical changes. | Delta Lake (SCD/MERGE); reference data sources | Delta Lake SCD/MERGE and reference data. | Approved business keys; reference data; history requirement | Approved keys, reference data and history rules exist. | Business team reviews matching and history rules
Curation Build | Cleaning and standardizing data (Silver). | Publish curated/base data product | Publish the cleaned data product for others to use. | Unity Catalog (data products); Delta Lake | Unity Catalog data products and Delta Lake. | Completed Silver transformations; technical tests | Silver transforms are done and tested. | Register metadata, ownership and consumption guidance
Composition Build | Building business-ready data (Gold). | Build Gold business transformations and aggregations | Build the business-ready calculations and summaries. | Azure Databricks; Databricks SQL; Delta Lake | Databricks, Databricks SQL and Delta Lake. | Curated data product; approved business logic | The curated product and approved business logic exist. | Trace each derived field to an agreed rule
Composition Build | Building business-ready data (Gold). | Create consumption-ready tables and views | Create the final tables and views consumers use. | Databricks SQL; Unity Catalog | Databricks SQL and Unity Catalog. | Confirmed consumer pattern and access model (e.g. MCP DataLayer for POD 1) | The consumer pattern/access model is confirmed (e.g. the MCP data service POD 1 uses). | Use semantic output only if confirmed for the MVP
Composition Build | Building business-ready data (Gold). | Optimize MVP queries and table layout | Tune the queries and tables for speed. | Databricks SQL; Delta (OPTIMIZE / Z-ORDER / liquid clustering) | Databricks SQL and Delta optimisation features. | Representative queries; expected workload | You have real queries and know the workload. | Capture baseline and post-optimization observations
Integration & Security | Wiring up secure access. | Configure service connectivity using approved identity pattern | Connect services securely using approved identities. | Managed Identity; APIM; Azure Key Vault | Managed Identity, API management and a secrets vault. | Endpoint details; identity and security approvals | Endpoint details and identity/security sign-off. | Prefer Managed Identity; avoid embedded credentials
Integration & Security | Wiring up secure access. | Validate permissions and negative-access scenarios | Test that allowed access works and denied access is blocked. | Unity Catalog; Microsoft Entra ID | Unity Catalog and Entra ID. | Approved role matrix; test identities | An approved role matrix and test accounts. | Infra and data platform teams review access behavior
Testing | Checking everything works and numbers match. | Create and execute unit tests | Write and run small tests on the code. | Databricks notebooks; test framework (pytest / Nutter) | Databricks and a test framework (pytest/Nutter). | Completed code; synthetic or approved test data | Finished code and test data exist. | Cover transformation, error and restart paths
Testing | Checking everything works and numbers match. | Execute system integration testing | Test the whole pipeline working together. | Azure Databricks; source and downstream endpoints | Databricks with source and downstream systems. | Integrated pipeline; SIT test cases; expected results | The pipeline is integrated and SIT cases/results exist. | Use the agreed shared Dev namespace for SIT
Testing | Checking everything works and numbers match. | Execute end-to-end data reconciliation | Check the numbers match from source to final output. | Databricks SQL; reconciliation queries | Databricks SQL and reconciliation queries. | Source totals; Bronze, Silver and Gold outputs | Source totals and all three layer outputs exist. | Record variances, causes and resolution
Testing | Checking everything works and numbers match. | Support business UAT and show-and-tell | Help the business test and demo the output. | Databricks SQL; dashboards or query outputs | Databricks SQL and dashboards/outputs. | Technical test exit; business scenarios; sample data | Technical testing is done and scenarios/data exist. | Use the agreed shared Dev namespace for UAT
Testing | Checking everything works and numbers match. | Resolve defects and prepare test exit evidence | Fix bugs and gather proof testing passed. | GitLab issues; test evidence repository | GitLab issues and an evidence repo. | Defect log; retest results; residual risks | A defect log, retest results and known risks exist. | Obtain data platform and business acceptance
CI/CD & Release | Packaging and releasing to production. | Create build and deployment pipeline | Build the automated build-and-deploy pipeline. | GitLab CI/CD; Databricks Asset Bundles / deployment tooling | GitLab CI/CD with Databricks Asset Bundles. | Repository; environment variables; deployment permissions | A repo, env variables and deploy permissions exist. | Align with the DevOps-managed pipeline
CI/CD & Release | Packaging and releasing to production. | Configure code quality and merge controls | Set code-quality checks and review rules for merging. | GitLab; linting and test tools | GitLab with linting and test tools. | Branching standard; reviewer list; quality gates | A branching standard, reviewers and quality gates exist. | Require peer review before merge
CI/CD & Release | Packaging and releasing to production. | Prepare release notes, implementation and rollback plan | Write the release notes and a rollback plan. | Release templates; GitLab | Release templates and GitLab. | Approved UAT; deployment sequence; support contacts | UAT is approved and the sequence/contacts are set. | Configuration file is intentionally omitted
CI/CD & Release | Packaging and releasing to production. | Deploy MVP assets and permissions | Deploy the notebooks, jobs, tables and permissions. | GitLab CI/CD; Azure Databricks; Unity Catalog (grants) | GitLab CI/CD, Databricks and Unity Catalog grants. | Release approval; production or confirmed target environment | Release approved and the target environment confirmed. | Deploy notebooks, jobs, tables, views and grants
CI/CD & Release | Packaging and releasing to production. | Execute post-deployment smoke test and reconciliation | Quick-check after deploy that it works and numbers match. | Azure Databricks; Databricks SQL | Databricks and Databricks SQL. | Successful deployment; test checklist | A successful deploy and a test checklist. | Confirm schedules, access and business output
Operations & Handover | Running it day-to-day and handing over. | Configure monitoring, alerting and run logging | Set up monitoring, alerts and run logs for operations. | Azure Monitor + Databricks job monitoring; emit data-product access/audit events to POD 2 (GERNAS/Beacon) where applicable | Azure Monitor & Databricks job monitoring, feeding data-access events to POD 2 where relevant. | Operational thresholds; support distribution list; agent-observability contract with POD 2 agreed | Agreed alert thresholds, a support list, and the POD 2 observability contract. | Assess agent observability only where applicable